## SurferUpdateTracking
Surfer Updates Tracking
Site name | Surfer Version | Update Date | Uwamp Version | Mysql Version | Work assigned by | Work related to | Chages applied | Comments
WRO5 | 2.3.0 | 2025-05-15 | 2.2.1 | 5.6.11 | Paul Casey | Modernization | Added new 4 chutes | Four new chutes have been added: M01190, M01192, M01015, and M01013.
DHL_BES1 | 3.0.1 | 2025-03-22 | 2.2.1 | 5.6.11 | Marco petrera | Harmonization | Updated the new Surfer Version (NXT) | We attempted to install the new Surfer NXT release, but the PC is incompatible with Uwamp 3.1.0 and MySQL 5.7.11, so we reverted to version 2.2.1.
DHL_BES1 | 3.0.1 | 2025-05-05 | 2.2.1 | 5.6.11 | Marco petrera | Harmonization | Moved surfer application from physical PC to Virtual PC | The Surfer application was migrated from the physical PC to a virtual machine.
DHL_BES2 | 3.0.1 | 2025-03-31 | 2.2.1 | 5.6.11 | Marco petrera | Harmonization | Updated the new Surfer Version (NXT) | The Surfer NXT version has been successfully installed
DHL_BES2 | 3.0.1 | 2025-05-09 | 2.2.1 | 5.6.11 | Marco petrera | Harmonization | Moved surfer application from physical PC to Virtual PC | After cloning the VM, Surfer failed to run. We recommended provisioning a fresh VM instead of cloning, then moved the application from the physical PC to that new virtual instance.
DHL_BES3 | 3.0.1 | 2025-05-05 | 2.2.1 | 5.6.11 | Marco petrera | Harmonization | Updated the new Surfer Version (NXT) | The Surfer NXT version has been successfully installed
DHL_BES3 | 3.0.1 | 2025-05-13 | 2.2.1 | 5.6.11 | Marco petrera | Harmonization | Updated the new Surfer Version (NXT) | After cloning the VM, Surfer failed to run. We recommended provisioning a fresh VM instead of cloning, then moved the application from the physical PC to that new virtual instance.
DHL_ASHS1
DHL_ASHS2
DHL_ASHS3
DHL_PZS1
DHL_PZS2
DHL_PZS3
AMAZON_SBN1
AMAZON_DTM1 | 1.0.0 | 2025-05-15 | 2.2.1 | 5.6.11 | Andrea Mangialardo | Comissioning | Corrected message 57 configuration | We have a problem with alarm translation due to incorrect configuration of message 57.
AMAZON_DTM1
AMAZON_PSP3
AMAZON_YVR6
AMAZON_TRN3